## How to use
Express Autocare ERP — Test checklist
One row per thing to check, grouped into journeys that follow a car (and a staff member) through the whole system.
How to work | Go through the Checklist sheet top to bottom (Day column = suggested day). Do the step as the role in "Who", compare with "Expected result".
Fill in (yellow) | Status, Tested on, Notes and Issue ID on the Checklist sheet; every column on the Issues sheet. Everything else is fixed.
Status values | Pass · Fail · Blocked (could not test because of another problem) · N/A (not used by us). Leave empty = not tested yet.
When something fails | Set Status = Fail, add a row on the Issues sheet (ID I-001, I-002 …), and put that ID in the Issue ID column. Don't stop to report: send the Issues sheet after the week.
Priority (Issues) | Must fix = wrong numbers, data lost, blocks work · Should fix = works but confusing or slow · Nice to have = an idea.
Progress | The Summary sheet counts Pass / Fail / Blocked / not tested per journey by itself.
Test data | Use the TEST copy (eaerp_demo or a fresh copy), never live data. Demo logins: admin@ / manager@ / advisor@ / tech1@ / tech2@ / backoffice@ / parts@ / driver@ / marketing@expressautocare.in, password: password.
Don't wait for time | php artisan crm:run · crm:daily · customerapp:reminders · hr:close-attendance · hr:tracking run the timed jobs now. Keep php artisan schedule:work running anyway.
Phones | Use the https tunnel address (Installation Guide §3). Location, camera and app notifications do not work on plain http on phones.
Help | User Manual (docs/EAERP_User_Manual.pdf) for how each screen works; App Installation & Play Store Guide for the phones.
Legend
You fill in | Yellow cells
Pass | Row colour when the Status is Pass
Fail | Row colour when the Status is Fail
Blocked | Row colour when the Status is Blocked
N/A | Row colour when the Status is N/A

## Summary
Journey | Checks | Pass | Fail | Blocked | N/A | Not tested | Done %
0. Setup | 9 | 0 | 0 | 0 | 0 | 9 | 0%
1. Drive-in service-plan job (Purchases & Stock ON) | 29 | 0 | 0 | 0 | 0 | 29 | 0%
1b. Same job with Purchases & Stock OFF | 4 | 0 | 0 | 0 | 0 | 4 | 0%
2. Lead to booking (CRM) | 16 | 0 | 0 | 0 | 0 | 16 | 0%
3. Pickup & drop and home service (live location) | 13 | 0 | 0 | 0 | 0 | 13 | 0%
4. Accident / body shop | 5 | 0 | 0 | 0 | 0 | 5 | 0%
5. A staff week (attendance, leave, live map) | 13 | 0 | 0 | 0 | 0 | 13 | 0%
6. Month end: payroll and accounts | 10 | 0 | 0 | 0 | 0 | 10 | 0%
7. Customer app tour | 20 | 0 | 0 | 0 | 0 | 20 | 0%
8. Settings, masters and switches | 17 | 0 | 0 | 0 | 0 | 17 | 0%
9. Every role (what each one sees) | 10 | 0 | 0 | 0 | 0 | 10 | 0%
10. Things going wrong | 14 | 0 | 0 | 0 | 0 | 14 | 0%
Total | 160 | 0 | 0 | 0 | 0 | 160 | 0%
Counts update by themselves from the Status column of the Checklist sheet.

## Checklist
ID | Day | Section | Module | Who | What to do | Expected result | Where | Status | Tested on | Notes | Issue ID
0.01 | Day 1 | 0. Setup | Setup | Owner | Use a TEST copy of the database (eaerp_demo or a fresh copy), never live data | You can create and cancel records freely | .env DB_DATABASE
0.02 | Day 1 | 0. Setup | Setup | Owner | npm run build, delete public\hot, start: php artisan serve --host 0.0.0.0 --port 8000 | Sign-in page opens on a phone on the same Wi-Fi | Installation Guide §2
0.03 | Day 1 | 0. Setup | Setup | Owner | Start the HTTPS tunnel (cloudflared) and set Settings › App Address & Customer App › Public address + APP_URL | Phones open the https address with a padlock; photos load | Installation Guide §3
0.04 | Day 1 | 0. Setup | Setup | Owner | Keep php artisan schedule:work running in a second window | Scheduled jobs run (reminders, location clean-up, attendance) | Command window
0.05 | Day 1 | 0. Setup | Setup | Owner | Check there is one login per role (Settings › Users & App Logins); create Body shop manager / advisor / technician and Marketing users if missing | Every role can sign in | Settings › Users
0.06 | Day 1 | 0. Setup | Setup | Owner | Settings › Branches: workshop location (lat/lng), radius, weekly off for each branch | Punching works only inside the radius | Settings › Branches
0.07 | Day 1 | 0. Setup | Setup | Owner | Settings › App Address & Customer App: UPI ID, payee name, helpline number | Saved; QR codes shown | Settings › App Address & Customer App
0.08 | Day 1 | 0. Setup | Setup | Owner | Install the staff APK on a driver phone and a technician phone (enter the tunnel address) | EA Workshop app signs in | Installation Guide §4
0.09 | Day 1 | 0. Setup | Setup | Owner | Optional: Settings › AI Assistant: add an Anthropic key, budget ₹200, switch on | Assistant available in the customer app | Settings › AI Assistant
1.01 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Customers | Advisor | Customers › New: name, mobile, source → Save → Add Vehicle (number, make, model, car type) → Create Job Card | Customer, car and job card created in one flow | Customers
1.02 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job card | Advisor | Job card: Service Type = a plan (e.g. EA Pro), Engine Oil Type, odometer, fuel level, customer complaints line by line → Save | Oil grades limited to those priced for the plan and car type; odometer and fuel required | Workshop › Job Cards › New
1.03 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job card | Advisor | Assign technicians (lead + others) and a bay right after creating | Technicians get a bell; bay shows on the job | Job card › Technicians & Bay
1.04 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Workshop | Advisor | Intake: trial drive notes + minimum arrival photos / videos | Job cannot move on until the minimum media is uploaded | Job card › Intake
1.05 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Workshop | Owner | Watch the stage move by itself as steps are done (Next Step box) | Status changes automatically; Next Step says what it waits for | Job card header
1.06 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job sheet | Technician | My Jobs › open the job sheet: mark activities Done / N/A; add photos where marked *** | Media-required activities refuse Done without the photo/video; N/A needs no media | My Jobs › Job sheet
1.07 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job sheet | Technician | Flag an activity with ⚠ (problem found) | It becomes a line in Additional Issues | Job sheet
1.08 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job sheet | Technician | Additional Issues: add a finding with a photo of the faulty part FIRST, then Parts Required, then Submit to SA for Parts | Advisor gets the parts request; technician sees no prices | Job sheet › Additional Issues
1.09 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Parts | Advisor | Review the technician's parts and forward them to the parts coordinator | Parts Desk shows the request | Job card › Parts
1.10 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Parts | Parts coordinator | Parts Desk: enter supplier, GST-inclusive cost; margin % applied | Advisor, owner and managers get a bell with the prices (not the technician) | Parts & Stock › Parts Desk
1.11 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Estimate | Advisor | Estimate: plan lines + the additional part and labour (from the labour charges master); discount; Send | Customer message prepared (share link); cost and margin never shown to the customer | Job card › Estimate
1.12 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Estimate | Customer | Open the WhatsApp job link: approve one item, decline one, add a comment, Send | Advisor gets a bell; declined line shows under Observations as "Recommended but not approved by customer" | Customer job page /j/…
1.13 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Estimate | Advisor | Record a decision on the customer's behalf (with a note) | Logged with the note; the customer is informed | Estimate editor
1.14 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Purchases | Parts coordinator | Order the approved part; receive it on a GRN with a photo per part (GST bill or not, credit or cash) | Part shows received; technician and advisor get a bell | Parts & Stock › GRN
1.15 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Purchases | Technician | Mark the part Right / Wrong before fitting; then the fitted photo, then Done on the issue line | Fitted photo allowed only after the part arrived; activity ticked Done automatically | Job sheet › Additional Issues
1.16 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job sheet | Technician | Try to submit a sheet with an activity marked ✗ (not done) | Submit is blocked unless a manager overrides with a reason | Job sheet
1.17 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Job sheet | Technician | Observations tab: add one, Submit for Report | Advisor gets a bell; advisor can toggle "show to customer" | Job sheet › Observations
1.18 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Workshop | Advisor | Record Trial drive OK, then Washing done | Stage moves to Final QC | Job card
1.19 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Workshop | Manager | Final QC: 3 random hidden spot-check points with a photo taken within 30 s | A gallery picture or a late photo is refused | Job card › Final QC
1.20 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Customer gallery | Customer | Customer page: photos section by section (arrival, job sheet, before/after) | Advisor can hide a photo; QC photos are not shown | Customer job page
1.21 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Back office | Make bill (proforma) → check lines (plan lines with HSN) → Approve | Bill made only after final QC; it waits while a part is not on a GRN | Job card › Billing & Delivery
1.22 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Back office | Record an advance earlier, then a split payment (cash + UPI + card) | Each part recorded; balance correct | Billing › Record payment
1.23 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Customer | Customer app: Pay by UPI part of the balance and send a UTR | "Being checked" in the app; back office gets a bell | Customer app › Job
1.24 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Back office | Billing › UPI Payments to Confirm → Confirm & record | Payment recorded as UPI with the UTR; app shows Received | Billing › UPI Payments to Confirm
1.25 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Back office | Convert to tax invoice; download the PDF | GST extracted from inclusive prices; discount shown above taxable value | Billing › Invoices
1.26 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Billing | Advisor | Paid in full → gate pass issued by itself → Vehicle out | Job delivered; stage message prepared | Job card › Billing & Delivery
1.27 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Reports | Customer | Service report released (plans 360 / Elite) | Report PDF on the customer page | Customer job page
1.28 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | CRM | Customer | After delivery: thank-you message with 1-tap rating and referral link; rate the job | Rating shows in CRM › Insights & Feedback | Messages to Send / /c/… link
1.29 | Day 1 | 1. Drive-in service-plan job (Purchases & Stock ON) | Customer app | Customer | Customer app inbox shows the stage updates for this job | One item per stage, no duplicates | Customer app › Inbox
1b.01 | Day 2 | 1b. Same job with Purchases & Stock OFF | Modules | Owner | Settings › Modules: switch Purchases & stock OFF | GRN screens disappear from the menu | Settings › Modules
1b.02 | Day 2 | 1b. Same job with Purchases & Stock OFF | Parts | Parts coordinator | Mark a part Received on the Parts Desk (no GRN) | Technician and advisor get a bell; no Right/Wrong check needed | Parts Desk
1b.03 | Day 2 | 1b. Same job with Purchases & Stock OFF | Billing | Back office | Make the bill | Not blocked by GRNs | Job card › Billing
1b.04 | Day 2 | 1b. Same job with Purchases & Stock OFF | Modules | Owner | Switch Purchases & stock back ON | Menus return; nothing lost | Settings › Modules
2.01 | Day 2 | 2. Lead to booking (CRM) | CRM | Owner | Settings › Lead Sources & Webhooks: copy a webhook link and send a test lead (browser or Pabbly/Zapier) | Lead appears in Leads › Today, assigned round-robin | Settings › CRM
2.02 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Quick-add a lead from a phone call; also try CSV import | Duplicate phone joins the open lead instead of making a new one | CRM › Leads
2.03 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Leave a new lead uncalled past 15 minutes (or run php artisan crm:run) | Reminder bell; at twice the time the manager is alerted | Bell
2.04 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Log a call: outcome no answer / call back / interested | Next follow-up set by itself | Lead › Call
2.05 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Send prices: pick a plan and car type | Message has the plan, the price for that car type and a booking link | Lead › Send prices
2.06 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Messages to Send: send it by tapping (share link) | WhatsApp opens with the text; marked sent; logged on the lead | CRM › Messages to Send
2.07 | Day 2 | 2. Lead to booking (CRM) | CRM | Customer | Open the booking link, pick day and slot, Book | Booking "To confirm"; desk gets a bell | /c/… link
2.08 | Day 2 | 2. Lead to booking (CRM) | Bookings | Advisor | Confirm the booking; send the reminder (after 17:00 the day before, or crm:run) | Confirmation and reminder messages prepared | CRM › Bookings
2.09 | Day 2 | 2. Lead to booking (CRM) | Bookings | Advisor | Car arrived → job card form opens already filled from the booking | Customer, car and plan pre-filled | CRM › Bookings
2.10 | Day 2 | 2. Lead to booking (CRM) | Bookings | Advisor | Another booking: move it, then mark Did not come (or wait 3 h after the slot) | No-show recorded; lead follow-up continues | CRM › Bookings
2.11 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Close a lead as lost with a "not now" reason | Gentle messages every few weeks (journey) | Lead › Close
2.12 | Day 2 | 2. Lead to booking (CRM) | CRM | Marketing | Stop messages for a lead | No more marketing messages to that number | Lead › Stop messages
2.13 | Day 2 | 2. Lead to booking (CRM) | CRM | Owner | Settings › Journeys / Creatives: add a creative with an image and a caption; put it in a journey | Journey messages appear in Messages to Send on schedule (crm:run) | Settings › CRM
2.14 | Day 2 | 2. Lead to booking (CRM) | CRM | Owner | php artisan crm:daily: service due, insurance due, win-back | Leads / messages created for due customers | Command window
2.15 | Day 2 | 2. Lead to booking (CRM) | CRM | Owner | Insights & Feedback: sources, conversion, ratings, ad spend | Numbers match what you did | CRM › Insights & Feedback
2.16 | Day 2 | 2. Lead to booking (CRM) | Referral | Customer | A new customer comes in with an existing customer's referral link and gets the car delivered | Referrer gets the referral credit in their wallet | Customer app › Wallet
3.01 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Advisor | Job card (or booking) with Pickup & drop: address, slot; assign a driver | Pickup and drop trips created; driver gets a bell | Workshop › Pickups & Drops
3.02 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Driver | Staff app: punch in from the road (on a trip day) | Punch accepted outside the workshop | My Attendance
3.03 | Day 3 | 3. Pickup & drop and home service (live location) | Live location | Driver | Accept the location notice; lock the phone; drive / walk 10 minutes | Green "Sharing your location" line; notification while locked | Staff app
3.04 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Driver | My Trips › Start → Navigate | Maps opens to the customer | My Trips
3.05 | Day 3 | 3. Pickup & drop and home service (live location) | Customer app | Customer | Customer app › the job: driver on the map with distance and ETA; WhatsApp page shows "on the way" | Position updates about every 30 s | Customer app › Job
3.06 | Day 3 | 3. Pickup & drop and home service (live location) | Live map | Manager | People › Live Staff Map | Driver shows Moving, with the trip, battery and "Android app" | People › Live Staff Map
3.07 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Driver | Arrived → odometer, fuel, unlimited intake photos/videos → Collected | This counts as the intake; the advisor does not repeat it | Trip screen
3.08 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Driver | Collect money from the customer on the trip | Shows as money the driver holds (Staff Money) | Trip › Payment
3.09 | Day 3 | 3. Pickup & drop and home service (live location) | Trips | Driver | Drop: try before the gate pass, then after full payment; handover photos → Delivered | Drop refused until the gate pass exists | Trip screen
3.10 | Day 3 | 3. Pickup & drop and home service (live location) | Home service | Home technician | Home visit job: its own job sheet; close the visit with the photos asked for | Workshop-only activities hidden | My Trips › Home visit
3.11 | Day 3 | 3. Pickup & drop and home service (live location) | Billing | Back office | Pickup / drop / home charges on the bill | Charges from Settings › Pickup, Drop & Home Service | Bill
3.12 | Day 3 | 3. Pickup & drop and home service (live location) | Live map | Owner | Tap the driver: day route, km, stops, gaps; change the date | Route matches the drive | Live Staff Map
3.13 | Day 3 | 3. Pickup & drop and home service (live location) | Live location | Driver | Punch out | Sharing stops; map shows Punched out | My Attendance
4.01 | Day 3 | 4. Accident / body shop | Assistant | Customer | Customer app › Ask › Accident help: describe + 2 damage photos | Damage list, rough range from the body-shop guide, claim steps | Customer app › Ask
4.02 | Day 3 | 4. Accident / body shop | Assistant | Customer | Get it inspected | Body-shop lead created (source Customer app) with the summary | CRM › Leads
4.03 | Day 3 | 4. Accident / body shop | Body shop | Body shop advisor | Open a body-shop job card from the lead; Body Shop job sheet | Body Shop master activities used | Job card
4.04 | Day 3 | 4. Accident / body shop | Body shop | Body shop technician | Work the body-shop sheet with photos | As for mechanical sheets | My Jobs
4.05 | Day 3 | 4. Accident / body shop | Body shop | Body shop manager | Oversee body-shop jobs across branches | Sees body-shop jobs; QC and overrides | Job Cards
5.01 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Attendance | Technician | Punch in with a selfie inside the workshop | Accepted; "You are in" | My Attendance
5.02 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Attendance | Technician | Try punching 2 km away; try with location off; try a gallery photo | All three refused with a clear message | My Attendance
5.03 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Attendance | Technician | Punch out after 21:00 (shift ends 19:00) | OT counts only after the first hour past shift end | My Attendance › month
5.04 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Attendance | Manager | Add a missed punch with a reason; void a wrong punch | Day rebuilt; reason logged | People › Attendance Register
5.05 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Attendance | Owner | php artisan hr:close-attendance for yesterday | Absent / weekly off / holiday / leave filled; missing out-punch flagged | Command window
5.06 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Leave | Technician | Apply for leave (full day and half day) | Manager gets a bell | My Attendance › Leave
5.07 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Leave | Manager | Approve one, reject one | Employee gets a bell; balance updated; unpaid beyond balance | People › Leave Requests
5.08 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Live location | Marketing | First punch-in: location notice; then turn GPS off for 15 min | Live map shows No signal with the reason | Live Staff Map
5.09 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Live location | Manager | Employees › untick "Share live location" for one person | Their phone stops sending; map shows Not tracked | People › Employees
5.10 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Live location | Owner | Settings › Pay, OT, Statutory & Live Location: change interval / no-signal minutes | New values used | HR & Payroll masters
5.11 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Staff money | Back office | Record that the driver handed over customer money | Driver's held amount goes down | People › Staff Money & Advances
5.12 | Day 1–4 | 5. A staff week (attendance, leave, live map) | Advances | Back office | Give a salary advance with monthly recovery | Recovered on the next payslip | Staff Money & Advances
5.13 | Day 1–4 | 5. A staff week (attendance, leave, live map) | CRM | Owner | Put a marketing executive on leave | New leads skip them in round-robin | CRM › Leads
6.01 | Day 5 | 6. Month end: payroll and accounts | Payroll | Back office | Payroll › Work out a month | Days, OT, off-day pay, PT/PF/ESI, advance recovery, incentives calculated | People › Payroll
6.02 | Day 5 | 6. Month end: payroll and accounts | Payroll | Back office | Correct one payslip line with a reason; add a manual incentive | Change logged | Payroll run
6.03 | Day 5 | 6. Month end: payroll and accounts | Payroll | Owner | Finalise (after the month ends); reopen and finalise again | Only the owner can finalise | Payroll run
6.04 | Day 5 | 6. Month end: payroll and accounts | Payroll | Back office | Mark paid; employee downloads the payslip PDF | Payslip visible in My Attendance › Payslips | Payroll / My Attendance
6.05 | Day 5 | 6. Month end: payroll and accounts | Accounts | Back office | Add an expense (cash, bank, supplier on credit) | Posted to the books | Accounts › Expenses
6.06 | Day 5 | 6. Month end: payroll and accounts | Accounts | Back office | Cash deposited to bank (contra) and a journal voucher | Balances move correctly | Accounts
6.07 | Day 5 | 6. Month end: payroll and accounts | Accounts | Owner | Reports: P&L, balance sheet, cash & bank book, who owes, GST summary | Bills, payments, GRNs and payroll from earlier journeys appear | Accounts & Reports
6.08 | Day 5 | 6. Month end: payroll and accounts | Accounts | Owner | Lock last month; try to post into it | Posting refused | Settings › Chart of Accounts
6.09 | Day 5 | 6. Month end: payroll and accounts | Accounts | Owner | Switch Accounts OFF, record a payment, switch ON, Bring the books up to date | The payment is posted after the resync | Settings › Modules
6.10 | Day 5 | 6. Month end: payroll and accounts | Dashboard | Owner | Dashboard: jobs in progress, daily collection, billing till date, total outstanding | Matches the day's activity | Dashboard
7.01 | Day 4 | 7. Customer app tour | Sign-in | Customer | Open a WhatsApp job link → Open in the Express Autocare app | Signed in; that job opens | Customer job page
7.02 | Day 4 | 7. Customer app tour | Sign-in | Customer | On another phone: mobile number → Get my sign-in code | Told to ask the workshop (Interakt off) | /app/login
7.03 | Day 4 | 7. Customer app tour | Sign-in | Advisor | Customers › the customer › Customer app card: read out the code | Code + valid till shown; advisor got a bell | Customer page
7.04 | Day 4 | 7. Customer app tour | Sign-in | Customer | Enter a wrong code, then the right one; reuse the same code | Wrong and reused codes refused | /app/login
7.05 | Day 4 | 7. Customer app tour | Home | Customer | Home: active jobs with approvals / balance / on the way; cars with due dates | Correct numbers | /app
7.06 | Day 4 | 7. Customer app tour | Job | Customer | Approve / decline items in the app; "Why is this needed?" (assistant on) | Advisor sees the answers; explanation appears and is reused | Customer app › Job
7.07 | Day 4 | 7. Customer app tour | Cars | Customer | Add a car (number, make, model) | Appears on Home; a number already registered is refused | Customer app › Add a car
7.08 | Day 4 | 7. Customer app tour | Service book | Customer | Service book of a car with past visits; History PDF | Visits, observations, due dates; PDF downloads | Customer app › Car
7.09 | Day 4 | 7. Customer app tour | Booking | Customer | Book: plan at the car's price, pickup with address, day and slot | In CRM › Bookings as Booked online; desk bell | Customer app › Book
7.10 | Day 4 | 7. Customer app tour | Booking | Customer | My bookings › Cancel | Cancelled in CRM too | Customer app › Bookings
7.11 | Day 4 | 7. Customer app tour | Documents | Customer | Add insurance and PUC with expiry dates (photo) | Car's insurance/PUC dates update; visible to staff | Customer app › Documents
7.12 | Day 4 | 7. Customer app tour | Reminders | Owner | php artisan customerapp:reminders (car with service due soon, insurance in < 30 days) | Inbox reminders, written once | Command window
7.13 | Day 4 | 7. Customer app tour | Inbox | Customer | Inbox › turn on notifications; move a job to a new stage | Phone notification arrives (https needed) | Customer app › Inbox
7.14 | Day 4 | 7. Customer app tour | Wallet | Customer | Wallet: credit, referral code, Share my link | WhatsApp share opens with the link | Customer app › Wallet
7.15 | Day 4 | 7. Customer app tour | Assistant | Customer | Ask › What's wrong: a symptom + a warning-light photo; Book a visit | Urgency, causes, services with price ranges; booking notes pre-filled | Customer app › Ask
7.16 | Day 4 | 7. Customer app tour | Assistant | Customer | Ask about brakes failing / smoke | Advises to stop driving and call | Customer app › Ask
7.17 | Day 4 | 7. Customer app tour | Assistant | Owner | Settings › AI Assistant: this month's cost, questions, bookings, leads | Matches the questions asked | Settings › AI Assistant
7.18 | Day 4 | 7. Customer app tour | Install | Customer | Install the app (Android Chrome › Install; iPhone Safari › Add to Home Screen) | Icon "Express Autocare" opens /app | Phone
7.19 | Day 4 | 7. Customer app tour | Android | Customer | Install the customer test APK (built with the tunnel address) | Opens on the customer sign-in | Installation Guide §5.2
7.20 | Day 4 | 7. Customer app tour | More | Customer | Sign out | Back to sign-in; old session no longer works | Customer app › More
8.01 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Price Masters: change a plan price for one car type; Save changes bar | New estimates and the customer app use the new price; nothing auto-saves | Settings › Price Masters
8.02 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Labour charges master: change a rate | Used on the next estimate line | Settings › Price Masters
8.03 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Car classes & models: add a model with its car type | Available on vehicles and in the customer app | Settings › Price Masters
8.04 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Job Sheet Masters: activity media type (photo / video / both), N/A allowed | Job sheets follow it | Settings › Job Sheet Masters
8.05 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Job stages: set one stage to manual; edit its WhatsApp message; tick "notify customer" | Stage waits for a manual move; message text used; app inbox notified | Settings › Job Stages
8.06 | Day 5 | 8. Settings, masters and switches | Masters | Owner | General Repairs master: minimum photos / videos per issue line | Enforced on Additional Issues | Settings
8.07 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Observation remarks; parts margin % | Used on observations and parts prices | Settings
8.08 | Day 5 | 8. Settings, masters and switches | Masters | Owner | Pickup, Drop & Home Service: charges, policy text, minimum photos | Used on trips and bills | Settings
8.09 | Day 5 | 8. Settings, masters and switches | Masters | Owner | HR masters: shifts, holidays, leave types, incentive rules, statutory slabs | Used in attendance and payroll | Settings › HR & Payroll
8.10 | Day 5 | 8. Settings, masters and switches | Masters | Owner | CRM rules: call-back SLA, sending hours, referral reward, message texts, booking slots, lost reasons | CRM follows them | Settings › CRM
8.11 | Day 5 | 8. Settings, masters and switches | Modules | Owner | Switch CRM, Attendance & payroll, Accounts, Customer app off one at a time | Their menus and screens close; the rest keeps working; links still open | Settings › Modules
8.12 | Day 5 | 8. Settings, masters and switches | WhatsApp | Owner | Settings › WhatsApp › Templates: open a message, Copy the text for Interakt | Text has {{1}}, {{2}} in the listed order | Settings › WhatsApp
8.13 | Day 5 | 8. Settings, masters and switches | WhatsApp | Owner | Leave the provider on Share links | All messages keep working by tapping | Settings › WhatsApp
8.14 | Day 5 | 8. Settings, masters and switches | App address | Owner | Change the public address; check a new job link and the staff-app QR | Links use the new address | Settings › App Address & Customer App
8.15 | Day 5 | 8. Settings, masters and switches | Staff app | Driver | Staff app › Settings › Change server address | Setup screen opens; reconnects | Staff app
8.16 | Day 5 | 8. Settings, masters and switches | Users | Owner | Create a user with a phone-only login; reset a password; deactivate | Phone login works; deactivated user cannot sign in | Settings › Users
8.17 | Day 5 | 8. Settings, masters and switches | Roles | Owner | Roles & Access: remove one permission from a role | That menu / button disappears for that role | Settings › Roles
9.01 | Day 6 | 9. Every role (what each one sees) | Roles | Owner | Everything visible; Settings › Modules, WhatsApp, AI only for the owner | Nothing missing | Menu
9.02 | Day 6 | 9. Every role (what each one sees) | Roles | Manager | All branches' operations, approvals, QC, attendance, Live Staff Map | No owner-only settings | Menu
9.03 | Day 6 | 9. Every role (what each one sees) | Roles | Advisor | Bookings, job cards, estimates, parts review, delivery, customer codes | No payroll, no accounts settings | Menu
9.04 | Day 6 | 9. Every role (what each one sees) | Roles | Technician | My Jobs and job sheets only; no prices anywhere | Cannot see estimates or bills | Menu
9.05 | Day 6 | 9. Every role (what each one sees) | Roles | Driver | My Trips, My Attendance | Nothing else | Menu
9.06 | Day 6 | 9. Every role (what each one sees) | Roles | Parts coordinator | Parts Desk, GRN, stock, supplier dues | No customer prices editing beyond parts | Menu
9.07 | Day 6 | 9. Every role (what each one sees) | Roles | Back office | Billing, payments, UPI confirmations, accounts, payroll preparation | Cannot finalise payroll | Menu
9.08 | Day 6 | 9. Every role (what each one sees) | Roles | Marketing | Leads, follow-ups, messages, bookings | No workshop screens | Menu
9.09 | Day 6 | 9. Every role (what each one sees) | Roles | Body shop manager / advisor / technician | Body-shop work as the mechanical equivalents | Correct menus | Menu
9.10 | Day 6 | 9. Every role (what each one sees) | Common | Everyone | My Day, global search (Ctrl + K / magnifier), bell, branch selector, phone bottom bar, install as app | Work for every role | Top bar
10.01 | Day 6 | 10. Things going wrong | Billing | Back office | Take more money than the bill | "Refund due"; refund it or keep it as customer credit before the gate pass | Billing
10.02 | Day 6 | 10. Things going wrong | Billing | Customer | Pay a later job with the credit | Payment method Customer credit; balance falls | Billing
10.03 | Day 6 | 10. Things going wrong | Billing | Manager | Gate pass before full payment | Needs owner/manager and a reason | Billing
10.04 | Day 6 | 10. Things going wrong | Estimate | Advisor | Change the plan after sending the estimate | Plan/oil locked on the job card; changed on the estimate | Job card
10.05 | Day 6 | 10. Things going wrong | Workshop | Owner | Move a job stage by hand | Needs a reason; logged | Job card
10.06 | Day 6 | 10. Things going wrong | Workshop | Advisor | Cancel a job card | No bill or payments allowed afterwards | Job card
10.07 | Day 6 | 10. Things going wrong | Links | Customer | Open an expired / revoked job link | "Link not available" message | Customer page
10.08 | Day 6 | 10. Things going wrong | UPI | Customer | Send the same UTR twice; send more than the balance | Both refused | Customer app › Pay
10.09 | Day 6 | 10. Things going wrong | UPI | Back office | Reject a UPI request with a reason | Customer sees the reason and "Not found" | UPI Payments to Confirm
10.10 | Day 6 | 10. Things going wrong | Offline | Driver | Turn mobile data off for 10 min while punched in, then on | Positions queued and sent later; route has no hole | Live Staff Map
10.11 | Day 6 | 10. Things going wrong | Double tap | Everyone | Double-tap Save / Punch / Pay buttons | Only one record created | Any screen
10.12 | Day 6 | 10. Things going wrong | Validation | Advisor | Save forms with missing required fields | Clear messages; nothing half-saved | Any form
10.13 | Day 6 | 10. Things going wrong | Assistant | Customer | Ask more than the daily limit | "You've asked … times today" message | Customer app › Ask
10.14 | Day 6 | 10. Things going wrong | Phones | Everyone | Use the system on a small phone and on a desktop | No cut-off buttons or text | All screens

## Issues
Issue ID | Date | Checklist ID | Screen | Role | What I did | What I expected | What happened | Screenshot file | Priority | Status | Fixed in
I-001 (example) | 19-Oct | 1.21 | Job card › Billing | Back office | Clicked Make bill after final QC | Proforma created | Error "Send the estimate first" although it was sent | IMG_2041.jpg | Must fix | Open
I-001
I-002
I-003
I-004
I-005
I-006
I-007
I-008
I-009
I-010
I-011
I-012
I-013
I-014
I-015
I-016
I-017
I-018
I-019
I-020
I-021
I-022
I-023
I-024
I-025
I-026
I-027
I-028
I-029
I-030
I-031
I-032
I-033
I-034
I-035
I-036
I-037
I-038
I-039
I-040
I-041
I-042
I-043
I-044
I-045
I-046
I-047
I-048
I-049
I-050
I-051
I-052
I-053
I-054
I-055
I-056
I-057
I-058
I-059
I-060
I-061
I-062
I-063
I-064
I-065
I-066
I-067
I-068
I-069
I-070
I-071
I-072
I-073
I-074
I-075
I-076
I-077
I-078
I-079
I-080
I-081
I-082
I-083
I-084
I-085
I-086
I-087
I-088
I-089
I-090
I-091
I-092
I-093
I-094
I-095
I-096
I-097
I-098
I-099
I-100